PostMind AI

Studio

Pre-Production Planning Playbook

The 6-8 weeks between specification and code — how to run them

For v1.0 and v1.1 (Reference Library, Overlays, Slideshow, Auto-Image)

Prepared by Jabbar · PostMind AI · 27 September 2026

A structured plan for the pre-build phase.

Nine parallel workstreams, week-by-week timeline, and a go/no-go gate before code starts.

Corpus provenance confirmed: Scenario 1 (Licensed). TEMPLATE and INSPIRE modes both unlocked.

Contents

1. Where we are — Scenario 1 confirmed, what it unlocks

2. Planning philosophy and the 6-8 week window

3. Workstream A — Product and scope decisions

4. Workstream B — Legal, contracts, and compliance

5. Workstream C — Provider accounts and API access

6. Workstream D — Team, roles, and hiring

7. Workstream E — Infrastructure and DevOps

8. Workstream F — Design and UX validation

9. Workstream G — Corpus preparation (Feature A specific)

10. Workstream H — QA fixtures and beta customer recruitment

11. Workstream I — Risk register operationalisation

12. The pre-production timeline

13. The handoff package

14. Go / No-Go gate for code kickoff

# 1. Where we are — Scenario 1 confirmed, what it unlocks

## 1.1 The A2 answer

The 50,000-video corpus is confirmed as Scenario 1 — Licensed. The videos were purchased and are held under commercial licences that permit their use as generation references and templates. This is documented on the corpus source records and the licences are on file.

The rest of this document is written on that basis. Every planning item that would have been gated on the provenance answer is now unblocked.

## 1.2 What is unlocked

- Feature A — TEMPLATE mode. The full structural blueprint replay is on the table. Users can pick any library video and get a new video that follows the same shot count, pacing, transitions, and overlay timing with their own content.

- Feature A — INSPIRE mode. The lighter style-tag reuse is also on the table (this was always going to be on the table; it is called out for completeness).

- Original source visibility. The library UI can show source attribution to users on the browse screen ("originally licensed from Storyblocks / Envato / [source]") without exposure. This makes the library feel more transparent and reinforces the licence story.

- Marketing narrative. "50,000 professionally-produced reference videos, licensed for structural use — pick one, get one like it in your brand" is a clean pitch. No footnotes.

- Rollout unblocked. Feature A can ship in the middle of v1.1 as planned in the addendum, not later.

## 1.3 What remains to do on the corpus

Scenario 1 removes the show-stopper question; it does not remove operational work. The corpus still needs:

- Every video's licence terms documented in a per-item record before it goes into video_library_licenses (Workstream B).

- The physical asset delivery from the source to the S3 bucket Studio uses (Workstream G).

- The ingestion pipeline built and run against the corpus (Workstream G).

- Category taxonomy validation with a sample of the actual corpus content (Workstream G).

## 1.4 Outstanding decisions this playbook resolves

Six decisions were flagged as open at the end of v1.0 or the v1.1 addendum. This playbook drives them to resolution during Weeks 0-2:

| Decision | Who decides | Deadline | Section |
| --- | --- | --- | --- |
| Final subscription pricing per tier | Product + Finance | End of Week 2 | Workstream A |
| Launch platform subset (all 8 or start with 3?) | Product + Marketing | End of Week 1 | Workstream A |
| Corpus ingestion — in-house vs Twelve Labs | Engineering lead + Finance | End of Week 2 | Workstream A / G |
| Slideshow as Basic-tier default project type | Product | End of Week 1 | Workstream A |
| Voice cloning scope — Enterprise only or Plus tier too | Product + Legal | End of Week 3 | Workstream A / B |
| Target markets at launch (UK only, or UK + Nigeria) | Product + Marketing | End of Week 1 | Workstream A |

# 2. Planning philosophy and the 6-8 week window

## 2.1 Why plan for 6-8 weeks before code

The temptation is to hand engineering the spec on Monday and expect commits by Friday. That approach fails on services with the profile of Studio for four specific reasons:

- External dependencies have long lead times. Meta App Review, TikTok Content Posting API approval, YouTube quota increase, and X API tier subscription are each 2-6 weeks of clock time and are on the critical path to any customer publish. Starting them the week after code kickoff means engineering is idle at the end of Sprint 1 waiting for permissions.

- Legal work cannot be back-filled. Corpus licence documentation, Terms of Service updates, DPA templates, regional compliance (UK-DPA, EU-GDPR, Nigerian NDPR) — all of these need lawyer time and back-and-forth. Deploying to production with any of them missing is not an option.

- Infrastructure decisions compound. Postgres cluster sizing, S3 bucket layout with lifecycle rules, CDN configuration, Redis DB allocation, secret management — these get set once and are expensive to change. Getting them right before day 1 saves months of migration work later.

- UX validation costs money to skip. The overlay editor and the review screen are the two highest-risk UX surfaces. A design system that survives contact with real users beats one that ships and then gets rebuilt in Sprint 4.

## 2.2 What planning does NOT mean

- It does not mean writing more specs. The v1.0 spec (47 pages) and the v1.1 addendum (34 pages) are the specs. This playbook is about resolving decisions, opening accounts, engaging vendors, hiring the team, and standing up infrastructure — not writing more architecture documents.

- It does not mean idle engineering. Engineering leads participate in Workstreams A, D, E, F, G, and I. They read the specs, they build the corpus ingestion prototype, they scaffold the repo, they run technical spikes on the overlay renderer. They just do not build v1.0 production code yet.

- It does not mean waterfall. Every workstream runs in parallel; every deliverable is time-boxed; anything not ready at Week 8 is either descoped from v1.0 launch or flagged as a launch risk.

## 2.3 The nine workstreams

| Workstream | Owner | Effort (weeks × people) |
| --- | --- | --- |
| A. Product and scope decisions | Founder / Product lead | 6w × 0.5 person |
| B. Legal, contracts, and compliance | Legal counsel + Founder | 6w × 0.3 person + counsel hours |
| C. Provider accounts and API access | Founder + DevOps | 6w × 0.5 person |
| D. Team, roles, and hiring | Founder + Engineering lead | 4w × 0.3 person + recruiter |
| E. Infrastructure and DevOps | Engineering lead + DevOps | 6w × 1 person |
| F. Design and UX validation | Product + Designer | 6w × 1 person + designer |
| G. Corpus preparation (Feature A) | Engineering lead + ML/data engineer | 8w × 1 person |
| H. QA fixtures and beta recruitment | Product + QA | 4w × 0.5 person |
| I. Risk register operationalisation | Founder + Engineering lead | 2w × 0.3 person |

## 2.4 The output of planning

At Week 8, one artefact exists: the handoff package (Section 13). If it is complete, engineering runs Sprint 1 on Monday of Week 9 without waiting for anything. If any of it is missing, launch is at risk and the go/no-go gate (Section 14) surfaces it.

# 3. Workstream A — Product and scope decisions

## 3.1 Purpose

Engineering cannot build against "probably 8 platforms" or "we'll figure out pricing later". Every product decision that affects code has a deadline in the first two weeks.

## 3.2 Decision log

| ID | Decision | Options | Owner | Deadline |
| --- | --- | --- | --- | --- |
| A-01 | Launch platform subset | All 8 at GA / 3 at GA (TikTok, IG, YT) + rest in 6 weeks / phased 3 then 5 | Product + Marketing | End Week 1 |
| A-02 | Target markets at launch | UK only / UK + Nigeria / UK + EU / UK + US | Product + Marketing | End Week 1 |
| A-03 | Slideshow as Basic tier default | Yes (recommended) / No, keep AI video as default | Product | End Week 1 |
| A-04 | Subscription pricing per tier (Basic / Standard / Plus / Enterprise) | Confirm the spec figures £29 / £79 / £199 / custom, or revise based on cost model | Product + Finance | End Week 2 |
| A-05 | Corpus ingestion approach | In-house pipeline / Twelve Labs / hybrid (in-house structural + Twelve Labs search) | Engineering + Finance | End Week 2 |
| A-06 | Voice cloning tier gating | Enterprise only / Plus + Enterprise / Standard + Plus + Enterprise | Product + Legal | End Week 3 |
| A-07 | In-house Remotion composer timing | v1.0 / v1.1 / v2.0 (recommended: v2.0) | Engineering + Finance | End Week 2 |
| A-08 | Studio UI hosting mode | Standalone at studio.postmind.ai / embedded in PostMind at postmind.ai/studio (recommended: standalone) | Product + Engineering | End Week 2 |
| A-09 | Feature B (overlays) — ship in v1.0 or wait for v1.1? | v1.0 stretch / v1.1 early / v1.1 mid | Product + Engineering | End Week 2 |
| A-10 | Feature D scan cadence for launch | Monthly (recommended) / weekly / on-demand only | Product | End Week 2 |

## 3.3 Decision meeting cadence

- Weekly 60-minute product decision meeting for the whole planning window.

- Attendees: Founder, Product lead, Engineering lead, Marketing rep (for A-01, A-02), Finance rep (for A-04, A-07).

- Output per meeting: a one-page decision memo per decision resolved, filed in Notion / Confluence / equivalent.

- Decisions not resolved by their deadline escalate to founder for a call by end of that week — no meeting slippage.

## 3.4 Deliverables from Workstream A

- Decision Memo Pack — one page per decision, 10 memos, signed off.

- Updated pricing model spreadsheet reconciled against v1.0 Section 12 cost data.

- Updated scope statement — one page — that supersedes the v1.0 and v1.1 executive summaries on any point where a decision changed them.

- Launch platform subset locked in the specification's Publishing section.

# 4. Workstream B — Legal, contracts, and compliance

## 4.1 Purpose

Studio touches copyright, personal data, third-party platform ToS, and cross-border data transfer. Every one of these must have a signed-off position before customers touch the product.

## 4.2 Deliverables and deadlines

| ID | Deliverable | Owner | Deadline |
| --- | --- | --- | --- |
| B-01 | Corpus licence register — one row per source (not per video), with licence terms, expiry, allowed uses, evidence PDF filed | Legal + Ops | End Week 3 |
| B-02 | Per-item licence bulk load — CSV mapping every video_library row to a licence source row for the video_library_licenses table | Ops | End Week 4 |
| B-03 | Terms of Service update covering Studio: video generation, publishing on user's behalf, IP ownership of output, voice/likeness rules | Legal + Product | End Week 4 |
| B-04 | Privacy Policy update covering website scanning, image ingestion, business profile as personal data, AI providers as sub-processors | Legal + Product | End Week 4 |
| B-05 | Data Processing Agreement (DPA) template for Enterprise customers with the sub-processor list (30+ providers) | Legal + Product | End Week 5 |
| B-06 | Sub-processor list published on trust.postmind.ai — every provider named with data flow, region, contract link | Legal + Marketing | End Week 5 |
| B-07 | Deepfake and voice cloning policy documented — consent recording flow, restricted uses, enforcement | Legal + Product | End Week 4 |
| B-08 | Content moderation policy — what Studio will and will not generate; enforcement mechanism (Hive / Sightengine + human review) | Legal + Trust & Safety | End Week 5 |
| B-09 | Acceptable Use Policy update — election disinformation, medical claims, financial scams explicitly prohibited | Legal | End Week 4 |
| B-10 | Regional compliance — UK-DPA, EU-GDPR, Nigerian NDPR positions documented per data type | Legal | End Week 6 |
| B-11 | Copyright takedown procedure — 24h SLA, form at studio.postmind.ai/takedown, escalation to Trust & Safety | Legal + Trust & Safety | End Week 6 |
| B-12 | Platform ToS review — TikTok, IG, YT, X, LinkedIn, FB automated posting terms; documented positions | Legal + Engineering | End Week 6 |

## 4.3 Legal counsel engagement

- Estimated counsel hours across all 12 deliverables: 40-80 hours depending on complexity and revision cycles.

- If PostMind has an existing legal firm: brief them in Week 1 with the v1.0 spec, v1.1 addendum, and this playbook.

- If not: shortlist 3 firms with SaaS + AI experience in Week 1; select in Week 2.

- Weekly 30-minute counsel sync for the planning window.

## 4.4 What legal does NOT need to gate

Not everything blocks code. These items can proceed on best-practice defaults during the build and be formalised before customer launch:

- Enterprise DPA template — needed before first Enterprise sale, not before Basic launch.

- Regional compliance positions for markets not in launch scope — deferred until that market opens.

- Copyright takedown procedure automation — the form and email inbox exist by launch; automation of the workflow is a v1.1 item.

# 5. Workstream C — Provider accounts and API access

## 5.1 Purpose

Every provider named in the v1.0 spec (Section 6) and v1.1 addendum (Section A9) needs a live production account, an active API key, billing terms in place, and — for the platforms that require it — approved permissions. Some of these have long lead times; some cannot be started until the app exists; the sequencing matters.

## 5.2 Publishing platform access — the long-lead items

| Platform | What is needed | Lead time | Owner | Start by |
| --- | --- | --- | --- | --- |
| Meta (IG + FB) | Add publishing scopes to existing Engagement App Review — reels_publishing, instagram_content_publish, pages_manage_posts | 3-6 weeks | Engineering + Product | Week 1 |
| TikTok Content Posting API | Business account + app submission + full review (DIRECT_POST scope) | 4-8 weeks | Engineering | Week 1 |
| YouTube Data API v3 | Quota increase from 10k to 100k-500k daily units, verified branding | 2-4 weeks | Engineering | Week 2 |
| X (Twitter) API | Basic tier £180/mo confirmed; Pro £4200/mo evaluated for scale | Immediate (Basic) | Product + Finance | Week 2 |
| LinkedIn Marketing Developer Platform | Program membership application — required for organic video posting at scale | 2-4 weeks | Product + Marketing | Week 2 |
| Threads (Meta) | API access confirmation; may piggyback on Meta app | 1-2 weeks | Engineering | Week 3 |

## 5.3 AI provider accounts

| Provider | Purpose | Account tier for launch | Owner | Start by |
| --- | --- | --- | --- | --- |
| Runway | Text-to-video (Gen-4) | Enterprise (rate limits + support) | Engineering | Week 1 |
| Luma Labs | Text-to-video fallback | Standard, upgrade after beta | Engineering | Week 2 |
| Google Vertex AI (Veo) | Text-to-video for Plus/Enterprise | Standard GCP + Vertex AI enablement | Engineering | Week 2 |
| Kling / 302.ai wrapper | Text-to-video for long clips | Standard | Engineering | Week 3 |
| Pika | Text-to-video fallback | Standard | Engineering | Week 3 |
| Fal.ai + Replicate | Aggregator fallbacks for lower tier | Standard | Engineering | Week 2 |
| HeyGen | Avatars — talking heads | Business tier (custom avatar support) | Engineering | Week 1 |
| D-ID | Avatar fallback | Standard | Engineering | Week 2 |
| ElevenLabs | Voice + brand voice cloning | Creator tier (upgrade to Pro after beta) | Engineering | Week 1 |
| Azure Speech | Voice fallback | Standard, via existing Azure sub | DevOps | Week 2 |
| Suno | Music generation (commercial licence) | Pro Commercial | Engineering | Week 2 |
| Storyblocks | Stock video + music + images (extended for image lib) | Enterprise (annual) | Product + Finance | Week 1 |
| Pexels | Free stock images | API key + attribution | Engineering | Week 2 |
| Unsplash | Stock image fallback | API key | Engineering | Week 2 |
| Shotstack | Video composition | Production tier | Engineering | Week 2 |
| Creatomate | Composition fallback | Standard | Engineering | Week 3 |
| AssemblyAI | Captioning + library transcription | Standard, volume tier after beta | Engineering | Week 2 |
| OpenAI | DALL-E 3 for image gen; text-embedding-3-large for corpus | Standard, pre-paid credits | Engineering | Week 1 |
| Anthropic | Claude for ideation + script + business classification | Standard tier (existing PostMind account) | Engineering | Week 1 |
| Hive Moderation | Content safety scan on rendered videos | Standard, upgrade after beta | Engineering + Trust & Safety | Week 2 |
| Sightengine | Safety fallback | Standard | Engineering | Week 3 |
| Twelve Labs (if A-05 selects) | Video corpus indexing and semantic search | Business tier | Engineering | Week 3 (after A-05) |
| Browserless.io (if not self-hosting Playwright) | Headless browser for site scans | Standard, £150/mo | DevOps | Week 3 |

## 5.4 Account setup deliverables per provider

For every account in 5.2 and 5.3, the same checklist applies:

- Account created under a shared PostMind email alias (not any individual's personal address).

- Billing set up — company card or invoice terms with 30-day payment window.

- Production API key generated and stored in the secret manager.

- Staging API key generated separately, stored under a distinct namespace.

- Rate limits documented in the vendor register.

- Support contact and escalation path recorded.

- SLA / uptime commitment documented (or noted as best-effort).

## 5.5 The vendor register

A single spreadsheet holds every vendor, its purpose, its account owner, its keys' rotation dates, its monthly spend cap, and its status. Kept in the secret manager (not in Google Sheets — this is credentials-adjacent data).

## 5.6 Deliverables from Workstream C

- Vendor register — complete for all 30+ providers.

- Secret manager populated with 60+ keys (production + staging for each).

- Meta App Review submitted.

- TikTok Content Posting API submitted.

- YouTube quota increase submitted.

- LinkedIn Marketing Developer Platform submitted.

# 6. Workstream D — Team, roles, and hiring

## 6.1 Purpose

Studio requires specific engineering skills that may or may not exist in the current PostMind team. Identifying gaps in Week 1 and closing them by Week 6 prevents Sprint 1 from stalling on a missing hire.

## 6.2 Roles required for the v1.0 + v1.1 build

| Role | Count | Skills needed | When needed |
| --- | --- | --- | --- |
| Engineering Lead / Tech Lead | 1 | Node.js, Next.js, distributed systems, provider integration patterns; owns architecture | Week 0 (planning + build) |
| Backend / Pipeline Engineer | 2 | TypeScript, Prisma, Postgres, BullMQ, async job orchestration, external API integration | Week 4-6 for build start |
| ML / Data Engineer | 1 | Video processing (FFmpeg), embeddings (pgvector, OpenAI), LLM prompt engineering; owns Feature A ingestion pipeline | Week 3 for corpus prep + build |
| Frontend Engineer | 2 | React, Next.js App Router, video editor UX experience (overlay editor is highest risk) | Week 4-6 for build start |
| DevOps / Platform Engineer | 1 (0.5 FTE ok) | AWS or GCP, Postgres ops, Redis ops, S3 + CloudFront, observability stack | Week 1 (planning + build) |
| Product Manager | 1 | SaaS PM, spec-to-delivery, external vendor coordination | Week 0 |
| Product Designer | 1 | SaaS design systems, video / editor UX; owns overlay editor prototype | Week 1 |
| QA / Test Engineer | 1 (0.5 FTE ok) | Test automation, video content QA, provider mock frameworks | Week 4 |
| Trust & Safety Lead | 0.25 FTE | Content moderation policy, incident response | Week 3 |

## 6.3 Skills gap assessment — do this in Week 1

- For each role, name the person(s) currently on staff who could fill it.

- Gap = role with no viable current hire.

- For each gap: decide hire vs contract vs upskill existing person.

- Time-box: gaps not closed by end of Week 6 either descope from v1.0 or delay v1.0 launch.

## 6.4 Hiring plan for likely gaps

| Role | Likely to be a gap? | Recommendation |
| --- | --- | --- |
| ML / Data Engineer | Yes — Feature A ingestion is specialised | Hire (permanent) or bring in a contractor for the 8-12 week ingestion build |
| Frontend Engineer (video editor UX) | Likely yes — overlay editor is a niche skill | Hire specifically for editor experience; contractor route acceptable |
| Product Designer (video editor) | Likely yes | Contractor with CapCut / Descript / similar background; 8-week engagement |
| Trust & Safety | Fractional if not already | Fractional external consultant covering policy + incident response |

## 6.5 Recruitment logistics

- Hiring pipeline: JD published Week 1; first-round interviews Week 3; offers out Week 5; starts Week 6-8.

- For UK hires: 4-week notice period is typical; account for this in start date.

- For contractors: shorter lead time (1-2 weeks); consider for gaps needing to close fast.

- For Nigeria-based hires (if target market includes Nigeria): timezone overlap with UK is 0-1 hours — no rotational issue.

## 6.6 Team ceremonies

Before code starts, agree the operating rhythm so it exists from day 1:

- Standups: daily 15 min, async on Slack for anyone remote.

- Sprint planning: weekly for planning phase; every 2 weeks once code starts.

- Retrospective: end of each sprint, 30 min.

- Product decision meeting: weekly through planning; monthly after build starts.

- Provider health check: weekly during planning (chase vendor approvals); shifts to monitoring dashboard once code is live.

- On-call: not required in planning phase; set up rota before v1.0 Phase 2 (Core Pipeline).

## 6.7 Deliverables from Workstream D

- Skills gap assessment sheet — one row per role, current holder, gap flag.

- Hiring plan with named candidates by end of Week 3, offers by Week 5, starts by Week 6-8.

- Team operating manual — one page — covering ceremonies, communication channels, escalation.

- Named roles for every workstream in this playbook.

# 7. Workstream E — Infrastructure and DevOps

## 7.1 Purpose

Standing up the shared infrastructure that Studio needs so day 1 of build finds a working staging environment. Delayed infrastructure is the most common cause of a promising early-sprint velocity collapsing in Sprint 3.

## 7.2 Infrastructure deliverables

| ID | Item | Owner | Deadline |
| --- | --- | --- | --- |
| E-01 | Postgres cluster — same as PostMind, studio schema created, pgvector extension enabled, connection pool sized for 30 sustained | DevOps | End Week 3 |
| E-02 | Redis cluster — same as PostMind, DB 3 allocated to Studio with noeviction policy | DevOps | End Week 3 |
| E-03 | S3 buckets — three buckets (studio-assets, studio-renders, studio-thumbnails) with versioning, lifecycle rules from v1.0 Section 17.4, and encryption at rest | DevOps | End Week 4 |
| E-04 | CDN — CloudFront (or Fastly) distributions per bucket with signed-URL configuration | DevOps | End Week 4 |
| E-05 | S3 corpus bucket — studio-library-assets with restricted-access policy for ingestion pipeline | DevOps | End Week 4 |
| E-06 | Studio subdomain — studio.postmind.ai (public) and studio.internal (private) with TLS certs, ingress rules | DevOps | End Week 4 |
| E-07 | CI/CD pipeline — build, test, lint, deploy to staging on merge to main; production deploy gated on manual approval | DevOps + Engineering Lead | End Week 5 |
| E-08 | Observability stack — logs (Datadog / Grafana), metrics (Prometheus), traces (OpenTelemetry), aligned with existing PostMind setup | DevOps | End Week 5 |
| E-09 | Secret manager — production and staging namespaces, IAM policies for who can read what | DevOps | End Week 3 |
| E-10 | Sentry project — Studio distinct from PostMind Core; source maps uploaded automatically | DevOps | End Week 5 |
| E-11 | Cost tracking — per-provider spend visible in real time; alerts at 80% / 100% of daily caps | DevOps + Finance | End Week 6 |
| E-12 | Backup and recovery — Postgres PITR, S3 versioning, Redis snapshots, documented recovery runbook | DevOps | End Week 6 |
| E-13 | Network policy — inbound rules for studio.postmind.ai (public), private ingress for studio.internal, outbound allow-list for provider APIs | DevOps + Security | End Week 5 |
| E-14 | KMS keys — per-org envelope encryption for platform tokens, voice profiles, and (Enterprise) BYOC provider keys | DevOps + Security | End Week 5 |

## 7.3 Sizing decisions to make in Week 1-2

- Postgres: Studio's tables will grow to ~40M rows/year at target scale. Recommend 8 vCPU / 32GB RAM / 1TB SSD for production, half that for staging. Cluster with 1 replica minimum.

- Redis: BullMQ + rate-limit counters at target scale ~500MB. Recommend 2GB with persistence enabled.

- S3: rough growth projection 15TB/year at target scale, dominated by video renders. Lifecycle rules (v1.0 §17.4) keep this bounded.

- Compute: web pods 3 min, workers by queue (orchestration 3, assets 5, publish 3, scheduled 2, analytics 2). Kubernetes-native or ECS with autoscaling.

## 7.4 What to NOT build in planning

- Application code — that starts in Week 9.

- Full monitoring dashboards — the observability plumbing is in place; the specific dashboards come during build.

- Load-testing scaffolding — spec's k6 script exists; wire it up in v1.0 Phase 5 (Beta).

## 7.5 Deliverables from Workstream E

- Working staging environment on studio-staging.postmind.ai returning 200 on GET / (even if the app is a stub).

- Working production environment on studio.postmind.ai returning 200 on GET / (locked to allow-listed IPs until launch).

- Secret manager populated (from Workstream C).

- CI/CD deploying to staging on every merge to main.

- Postgres cluster with studio schema and pgvector.

- S3 buckets with lifecycle rules.

# 8. Workstream F — Design and UX validation

## 8.1 Purpose

Two UX surfaces are high-risk enough to warrant validation before build: the overlay editor and the review screen. The rest of the UI is standard SaaS design work but should still be prototyped before it hits engineering.

## 8.2 Design deliverables

| ID | Deliverable | Format | Owner | Deadline |
| --- | --- | --- | --- | --- |
| F-01 | Design system alignment audit — does Studio use PostMind's existing tokens or need extensions? | 1-page report | Designer + Engineering | End Week 2 |
| F-02 | Wireframes — Create screen (New Project) including all four source types | Figma | Designer | End Week 3 |
| F-03 | Wireframes — Review screen with per-variant preview, shot strip, quality panel | Figma | Designer | End Week 3 |
| F-04 | Wireframes — Manage (projects, publications, analytics, calendar) | Figma | Designer | End Week 4 |
| F-05 | Wireframes — Library browse and detail (Feature A) | Figma | Designer | End Week 4 |
| F-06 | Overlay editor high-fidelity prototype — clickable, feels real | Figma prototype + testing kit | Designer | End Week 5 |
| F-07 | Slideshow builder wireframes (Feature C) | Figma | Designer | End Week 4 |
| F-08 | Business profile / image library screens (Feature D) | Figma | Designer | End Week 5 |
| F-09 | Admin Centre extensions — kill switch, queue health, cost dashboard, safety review queue | Figma | Designer | End Week 5 |
| F-10 | User research — 5 interviews with target customers (mix of persona types from v1.0 §3.3) | Research report + video recordings | Product + Designer | End Week 6 |
| F-11 | Overlay editor usability test — same 5 interviewees walk through the prototype | Usability report with issues log | Product + Designer | End Week 7 |

## 8.3 The overlay editor — why it needs a prototype

The overlay editor is the single UX surface most likely to eat weeks of engineering time if got wrong. Real-time WYSIWYG on video is a common quality trap — the HTML/CSS preview and the final Shotstack render will disagree in subtle ways. Prototyping this before build reveals:

- Which overlay parameters users actually change (font size, color) versus which they never touch (letter spacing, easing) — informs default UI vs advanced-panel split.

- Whether the preset library is the right on-ramp, or whether "start from blank" needs to be equally prominent.

- How users think about timing — via scrubber, via drag on shot strip, via numeric input?

- What happens when the prototype's preview disagrees with what the final render will show — the acceptable divergence threshold.

Skipping the prototype adds 2-3 weeks to the editor build in Sprint 4-6. Doing the prototype is a 2-week investment in planning.

## 8.4 User research plan

- Recruit 5 target customers matching v1.0 personas: 2 solo creators, 2 SMB marketing owners, 1 agency.

- Each interview: 60 min, structured around three tasks — create a video from a brief, edit a text overlay, review a rendered result.

- Compensation: £75 per interviewee via Amazon voucher or equivalent.

- Output: research report with 10 specific product recommendations by end of Week 6.

## 8.5 Deliverables from Workstream F

- Complete Figma file with all screens for v1.0 + v1.1 wireframed to component fidelity.

- Clickable prototype of the overlay editor validated with 5 users.

- User research report with product recommendations rolled into decisions log (Workstream A).

- Design system extensions defined and shared with Engineering.

- Signed-off screens for Sprint 1 (Create screen, Review screen shell) at Week 6.

# 9. Workstream G — Corpus preparation (Feature A specific)

## 9.1 Purpose

Scenario 1 confirmed means the corpus can be used. It does not mean the corpus is ready. Fifty thousand licensed videos need to be physically delivered, catalogued with per-item licence status, uploaded to S3, ingested through the analysis pipeline, and validated for search quality — before Feature A ships. This workstream runs the longest of the nine (8 weeks) and is the tightest on the critical path to Feature A.

## 9.2 The corpus preparation stages

| Stage | Deliverable | Duration | Owner |
| --- | --- | --- | --- |
| G.1 Delivery | 50k video files landed in studio-library-assets S3 bucket with per-file metadata CSV | Week 1-3 | Ops + Vendor |
| G.2 Licence documentation | Per-source licence register (Workstream B) linked to per-item licence rows | Week 2-4 | Legal + Ops |
| G.3 Category seeding | 200-node category taxonomy validated against a 500-video sample, refined where reality diverges from spec | Week 3-4 | Product + ML engineer |
| G.4 Ingestion prototype | Ingestion pipeline running against 100 sample videos, output reviewed | Week 4-5 | ML engineer |
| G.5 Ingestion pipeline hardening | Prototype productionised — error handling, retries, idempotency, monitoring | Week 5-6 | ML engineer + Backend |
| G.6 Full ingestion run | All 50k videos ingested; video_library, video_library_analysis, video_library_embeddings populated | Week 6-8 | ML engineer (automated) |
| G.7 Search quality validation | Sample 200 videos across categories; test similarity + business-to-video queries; tune weightings | Week 7-8 | ML engineer + Product |

## 9.3 A-05 decision — in-house vs Twelve Labs

This decision (due end of Week 2) shapes G.4 onward. The trade-off:

| Aspect | In-house pipeline | Twelve Labs |
| --- | --- | --- |
| Engineering effort | 8-12 weeks build + ongoing | 1-2 weeks integration |
| Per-video ingestion cost | £0.05-£0.15 (external APIs only) | ~£0.10 per 30s video |
| Ongoing per-search cost | Free (pgvector on our infra) | Per-query cost |
| Control over structural analysis | Full — LLM prompt we own | Limited to their outputs |
| Ingestion completion time | 6-8 weeks | 2-3 weeks |
| Scaling to 100k+ videos | Straightforward (pgvector scales fine) | Cost grows linearly |
| Recommendation | Build in-house if corpus expected to grow past 100k or if the structural blueprint needs customisation Twelve Labs cannot match. Otherwise use Twelve Labs to compress the schedule. |  |

## 9.4 The ingestion prototype (G.4) — 100-video test

Before running against all 50k, prove the pipeline on 100. This catches:

- Bad shot detection thresholds that produce nonsense blueprints.

- OCR failures on non-standard fonts or motion-blurred text.

- Music tempo detection failing on tracks with variable BPM.

- LLM structural analysis outputs that don't match the schema.

- Embedding model producing collapsed / unhelpful neighbours.

The 100-video test is human-reviewed shot-by-shot. Any category where the pipeline fails on >10% of videos triggers a fix before proceeding to full ingestion.

## 9.5 Category taxonomy validation

The v1.1 addendum ships a 200-node seed taxonomy. It is a good starting point; it is not the answer. During Week 3-4, validate:

- Are there categories in the corpus that don't map to any seed node? Add them.

- Are there seed nodes that no corpus video fits? Consider removing (users won't find matches anyway).

- Are there sub-niches over-represented in the corpus (say, fitness has 8000 videos, cat products has 12)? Rebalance or note the imbalance in UI.

- Is auto-classification confident (>0.7 top-choice) on 90%+ of videos? If not, revise the classification prompt.

## 9.6 Ingestion cost and time

- Per-video cost (in-house): £0.05-£0.15 depending on duration. 50k × £0.10 median = £5,000 one-off.

- Per-video wall-clock time: 2-5 minutes. Parallelised at 20 concurrent jobs = ~150-400 hours = 6-16 wall days.

- Budget the full 2-3 weeks for ingestion run (G.6) to allow for retries, model iterations, and reviewer feedback.

## 9.7 Deliverables from Workstream G

- 50k videos physically in the S3 bucket.

- Per-item licence status recorded in video_library_licenses.

- Validated category taxonomy (seed edited based on corpus reality).

- Ingestion pipeline running in production.

- 50k video_library, video_library_analysis, video_library_embeddings rows populated.

- Search quality report showing similarity queries return sensible neighbours in tested categories.

# 10. Workstream H — QA fixtures and beta customer recruitment

## 10.1 Purpose

A launch works when the first 20 customers have a positive experience, not when the code is technically correct. This workstream sets up the fixtures QA needs to validate the build and identifies the 20 people who will experience v1.0 first.

## 10.2 Fixtures needed by QA

| ID | Fixture | Purpose | Owner | Deadline |
| --- | --- | --- | --- | --- |
| H-01 | Test brand kits — 5 varieties across industries | Regression testing brand-substitution logic | Product + Designer | End Week 5 |
| H-02 | Test brief library — 20 sample briefs from real customer types | Ideation regression | Product | End Week 5 |
| H-03 | Test websites for Feature D — 20 sites across industries with known correct classifications | Business-classification accuracy testing | Product + QA | End Week 6 |
| H-04 | Test voice samples — 3 consented voice clones for Feature B voice testing | Voice profile regression | Product | End Week 6 |
| H-05 | Test connected platform accounts — Studio-owned test accounts on all 8 platforms | Publishing regression without touching customer accounts | DevOps + Product | End Week 6 |
| H-06 | Test video-library references — 100 curated corpus items covering all category types | TEMPLATE and INSPIRE regression | Product + ML | End Week 7 |
| H-07 | Golden-path test scenarios — 15 end-to-end journeys | Sprint-end regression checkpoint | QA + Product | End Week 6 |
| H-08 | Failure-injection test cases — bad provider responses, rate-limit triggers, safety-flag triggers | Resilience regression | QA + Engineering | End Week 7 |

## 10.3 Beta customer recruitment

v1.0 Phase 5 (v1.0 Section 19) is a 6-week beta with 20-50 friendly customers. Recruit them during planning so they're ready when the code is.

| Cohort | Size | Persona mix | Recruitment channel | Deadline |
| --- | --- | --- | --- | --- |
| Alpha (Phase 1) | 5-10 | Internal PostMind team + 3-5 super-friendly external accounts | Direct outreach | End Week 4 |
| Beta (Phase 5) | 20-50 | Solo creators (10), SMB marketing (15), agencies (5), enterprise pilot (5-10) | PostMind existing customer base + waitlist + industry networks | End Week 6 |

## 10.4 Beta customer commitments

- 30-day free access to Studio Plus tier.

- Weekly 15-min feedback call for the first 4 weeks.

- Access to a private Slack / Discord channel with the Studio team.

- NDA covering pre-release features.

- In exchange: honest feedback and (optional) case-study permission.

## 10.5 Deliverables from Workstream H

- Fixture library ready for QA (Week 6-7).

- Alpha customer list signed (Week 4).

- Beta customer list signed (Week 6).

- Feedback channel infrastructure (Slack / Discord + form) live (Week 6).

# 11. Workstream I — Risk register operationalisation

## 11.1 Purpose

The v1.0 spec (Section 20) and v1.1 addendum (Section A13) list 22 risks between them. Listing risks is not managing them. This workstream turns each listed risk into a monitored, owned, escalation-defined item before code kickoff.

## 11.2 Risk register operational format

Every risk from v1.0 §20 and v1.1 §A13 is upgraded to include:

- Owner — single named person accountable for monitoring and response.

- Monitoring metric — the specific dashboard number that indicates the risk is materialising.

- Alert threshold — the value at which the risk is escalated.

- Escalation path — who is paged, in what order, at what threshold.

- Mitigation runbook — the specific steps to take when the risk materialises.

- Review cadence — how often the risk is reassessed.

## 11.3 Priority risks needing runbook by Week 8

| Risk | Metric | Alert threshold | Runbook status by W8 |
| --- | --- | --- | --- |
| Provider outage during generation window | Per-provider circuit breaker state | 1+ providers OPEN | Written + rehearsed |
| Cost runaway (per-org daily cap) | cost_per_org_day / daily_cap | >80% | Written + auto-response tested |
| Content safety false negative published | Hive scan miss rate on periodic audit | Any true miss in monthly audit | Written + Trust & Safety on-call |
| Publishing platform API breaking change | Adapter integration test daily result | 1+ tests failing | Written + hotfix rota |
| Corpus search quality degradation | Human-graded relevance on weekly sample | <80% relevant top-5 | Written + retraining plan |
| Website scan blocked by anti-bot | Scan failure rate by target | >10% failure rate on any customer | Written + fallback (Playwright, stock-only) defined |
| Meta / TikTok / YouTube account revocation | Platform account status daily | Any account in warning state | Written + emergency comms drafted |
| Storage cost balloon | S3 bill weekly | >125% of forecast | Written + lifecycle audit |

## 11.4 Kill switch and rollback rehearsal

Both v1.0 (Section 12) and the shared PostMind kill-switch pattern from Engagement require the switch to work under load. Before code launch, rehearse:

- Global kill switch — toggle from Admin Centre; verify all queues drain and all publishing halts within 60 seconds; verify graceful UI state.

- Workspace freeze — toggle one org; verify their generations pause; verify other orgs continue.

- Per-provider disable — toggle Runway off; verify router fails over to Luma.

- Rollback — revert last deploy on staging; verify DB migrations don't break; verify subsequent redeploy works.

Every rehearsal is timed. Any that takes longer than its SLO (60s for kill switch, 5 min for rollback) is a blocker.

## 11.5 Deliverables from Workstream I

- Consolidated risk register with all 22 risks upgraded to operational format.

- Runbooks for the 8 priority risks written and stored in the ops wiki.

- On-call rota drafted (activates from v1.0 Phase 2).

- Kill-switch and rollback rehearsals executed on staging with times documented.

# 12. The pre-production timeline

## 12.1 Week-by-week view

The nine workstreams run in parallel. This table shows the anchor deliverable per workstream per week. Empty cells mean the workstream is either not yet active or in continuous execution against a longer deliverable.

| Wk | A Product | B Legal | C Vendors | D Team | E Infra | F Design | G Corpus | H QA/Beta | I Risk |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0 | Kickoff | Counsel engaged | Register drafted | Gap assessment | Sizing decisions | System audit start | - | - | - |
| 1 | A-01 A-02 A-03 | Corpus licence source docs | Meta / TikTok / YT / X submissions | JDs published | Postgres + Redis | Wireframe start | Delivery start | - | - |
| 2 | A-04 A-05 A-07 A-08 | - | AI provider accounts live | First interviews | S3 + CDN + subdomain | Wireframes 50% | Delivery cont. | - | - |
| 3 | A-06 A-09 A-10 | ToS + Privacy draft | LinkedIn + Threads | Offers out | Secret mgr + CI start | Overlay proto start | Category validation | Alpha list | Owners assigned |
| 4 | Memos signed | DPA + Sub-procs | Register complete | Contracts | CI to staging | Manage/Library WF | Ingestion proto | Fixtures start | Metrics defined |
| 5 | Scope finalised | AUP + Deepfake | Meta App Review | First hires start | Observability | Overlay proto done | Ingest hardening | Fixtures 60% | Runbook drafts |
| 6 | - | Regional compl. | - | Team at 80% | Cost + backup | 5 user interviews | Full ingest 50% | Beta list | KS rehearsal 1 |
| 7 | - | Takedown proc. | - | Team at 100% | - | Editor usability | Full ingest 90% | Golden-path scen. | Runbooks final |
| 8 | - | Platform ToS | - | - | Final hardening | Sign-off screens | Search quality QA | Fixtures done | KS reh. 2 + rollback |

## 12.2 Critical path

The longest chain of dependencies determines the earliest possible code kickoff. In order:

- Provider approvals (Workstream C) — Meta App Review (6 weeks) and TikTok Content Posting API (8 weeks) submissions filed in Week 1 finish around Week 7-9.

- Corpus ingestion (Workstream G) — 8 weeks end-to-end assuming in-house pipeline decision.

- Overlay editor design validation (Workstream F) — 7 weeks from wireframe start to validated prototype.

Any of these three chains slipping beyond Week 8 shifts the code-kickoff date to accommodate.

## 12.3 What can run late without shifting kickoff

- Some publishing platform approvals (LinkedIn, Threads, X Pro tier) can lag by 2-3 weeks past kickoff without blocking Sprint 1 — those platforms just come online later in the build.

- Enterprise DPA — first Enterprise customer is unlikely before Month 3 of build; can slip to Week 12.

- Beta customer full recruitment — first 5 alpha customers must be recruited; the remaining 15-45 can be added during build.

- Runbook rehearsal 2 — nice-to-have in planning; must-have before v1.0 Phase 5 (Beta).

## 12.4 Buffer weeks

The plan is 8 weeks. Reality has a way of consuming an extra 20%. Building in a 2-week buffer means:

- If everything hits by Week 8 — kickoff Monday Week 9. Bonus 2 weeks for team ramp-up, technical spikes, and Sprint 0.

- If key items slip by 2 weeks — kickoff Monday Week 11 without formal delay.

- If key items slip by more than 2 weeks — the go/no-go gate (Section 14) flags it; the team decides descope or delay.

# 13. The handoff package

## 13.1 Purpose

At Week 8, one single package moves from planning to engineering. If it is complete, Sprint 1 begins on Monday of Week 9 with zero friction. If it is missing anything, that item becomes the first blocker of the build. The point of the entire 8-week planning window is to make this package complete.

## 13.2 What is in the package

| Section | Item | Source workstream |
| --- | --- | --- |
| 1. Specifications | v1.0 spec, v1.1 addendum, this playbook — the canonical trio | - |
| 1. Specifications | Updated scope statement with all A-workstream decisions | A |
| 1. Specifications | Confirmed launch platform subset | A |
| 1. Specifications | Confirmed pricing model | A |
| 1. Specifications | Confirmed in-house vs Twelve Labs decision | A / G |
| 2. Legal | Corpus licence register | B / G |
| 2. Legal | Terms of Service, Privacy Policy, Acceptable Use Policy — final versions | B |
| 2. Legal | DPA template | B |
| 2. Legal | Sub-processor list ready for publication | B |
| 2. Legal | Content moderation and deepfake policies | B |
| 3. Infrastructure | Staging and production environments live at studio-staging.postmind.ai and studio.postmind.ai | E |
| 3. Infrastructure | Postgres cluster with studio schema and pgvector | E |
| 3. Infrastructure | Redis DB 3 allocated | E |
| 3. Infrastructure | S3 buckets with lifecycle rules | E |
| 3. Infrastructure | Secret manager populated with all 60+ API keys | C / E |
| 3. Infrastructure | CI/CD deploying to staging on merge to main | E |
| 3. Infrastructure | Observability stack live | E |
| 4. Provider access | Vendor register — all 30+ providers with keys, contacts, rate limits | C |
| 4. Provider access | Meta App Review submitted (approval likely in-flight) | C |
| 4. Provider access | TikTok Content Posting API submitted | C |
| 4. Provider access | YouTube quota increase submitted | C |
| 4. Provider access | LinkedIn Marketing Developer Platform submitted | C |
| 5. Team | Named engineering lead | D |
| 5. Team | Named backend engineers × 2 | D |
| 5. Team | Named ML/data engineer | D |
| 5. Team | Named frontend engineers × 2 | D |
| 5. Team | Named DevOps engineer | D |
| 5. Team | Named product manager, designer, QA | D |
| 5. Team | Team operating manual (ceremonies, escalation) | D |
| 6. Design | Signed-off Figma file for all v1.0 screens | F |
| 6. Design | Validated overlay editor prototype | F |
| 6. Design | User research report with product recommendations | F |
| 7. Corpus | 50k videos in S3 with per-item licence rows | G |
| 7. Corpus | Validated category taxonomy | G |
| 7. Corpus | Ingestion pipeline built and run (or Twelve Labs integration complete) | G |
| 7. Corpus | Search quality report | G |
| 8. QA | Test brand kits, briefs, websites, voice samples | H |
| 8. QA | Test connected platform accounts | H |
| 8. QA | Test video-library references | H |
| 8. QA | Golden-path scenarios | H |
| 8. QA | Alpha and beta customer lists | H |
| 9. Risk | Consolidated risk register with owners, metrics, thresholds | I |
| 9. Risk | Runbooks for 8 priority risks | I |
| 9. Risk | Kill-switch and rollback rehearsal reports | I |
| 10. Sprint 1 | Pre-written tickets in the tracker for Sprint 1 (Weeks 9-10) | Engineering Lead + PM |
| 10. Sprint 1 | Pre-written tickets for Sprint 2 (Weeks 11-12) | Engineering Lead + PM |

## 13.3 Sprint 1 pre-written tickets

The absolute smallest set of tickets that keep engineering moving in Week 9 without waiting for a planning meeting. Engineering Lead writes these in Week 7-8 as the last planning deliverable.

### Sprint 1 candidate scope

- Repo scaffold — Next.js 15 App Router, Prisma, TypeScript, ESLint, Prettier, Vitest.

- The four @/lib/* integration points from v1.0 Section 7 stubbed and wired to PostMind's staging JWKS.

- Prisma migrations for the studio schema — all v1.0 tables plus v1.1 additions in one migration set.

- Health endpoints (/api/health, /api/health/ready) implemented and returning correct states from staging.

- First provider adapter (Anthropic Claude for ideation) wired end-to-end.

- First worker (studio-orchestration with plan-project stub) deployed and consuming from BullMQ.

- Sentry + observability wired — a deliberate test error propagates to the dashboard.

### Sprint 2 candidate scope

- Ideation and Script layers (Layer 1-2 of the pipeline) end-to-end for one target platform (TikTok 9:16, 30s).

- Runway adapter wired, generating one AI clip end-to-end.

- ElevenLabs adapter wired, generating voice for one shot.

- Shot rows written to DB; project state transitions logged.

- Kill-switch table populated; all worker jobs check it.

## 13.4 Package format

- A single index page (Notion / Confluence / internal doc) with links to every artefact.

- Every linked artefact stored in a stable location (not a person's Google Drive).

- A one-page executive summary of the state of each of the 10 sections.

- A single go/no-go recommendation from the Engineering Lead and Founder.

# 14. Go / No-Go gate for code kickoff

## 14.1 Purpose

At end of Week 8, one meeting decides: begin Sprint 1 on Monday of Week 9, or slip. This section defines the criteria that meeting uses. Anything less rigorous than a written checklist tends to result in "looks fine, let's start" — followed by a stall in Sprint 3 when a missed dependency surfaces.

## 14.2 The go criteria

For a Go decision, every item below must be true. Items marked with an asterisk have documented workarounds if they cannot be met on time — the workaround must also be signed off.

| Criterion | Owner sign-off | Workaround if not met by W8 |
| --- | --- | --- |
| All 10 A-workstream decisions signed off and in the decision log | Product + Founder | None — must be resolved |
| Corpus licence register complete for all 50k videos | Legal + Ops | None — Feature A cannot ship without this |
| Terms of Service, Privacy Policy, Acceptable Use Policy in final draft (not necessarily published) | Legal | *Can be finalised during v1.0 Phase 1, must publish before Phase 5 Beta |
| Meta App Review, TikTok Content Posting API, YouTube quota, LinkedIn MDP submissions all filed | Product + Engineering | *Late submissions are recoverable; unfiled ones are not |
| Studio staging environment returning 200 on /api/health | DevOps | None — Sprint 1 cannot deploy without this |
| Studio production environment provisioned (locked to allow-list) | DevOps | *Can slip 1 week |
| All 30+ provider API keys in secret manager | DevOps + Engineering | *Secondary providers can slip 2 weeks |
| Full engineering team in place (Eng Lead, 2 backend, ML, 2 frontend, DevOps, PM, Designer, QA) | Founder + Eng Lead | *Up to 1 role can slip 4 weeks if the affected sprints are re-sequenced |
| Validated overlay editor prototype | Product + Designer | *Feature B can slip from v1.0 stretch to v1.1 without shifting v1.0 GA |
| 50k videos ingested through pipeline; search quality validated | ML Engineer + Product | *Feature A launch shifts to v1.1 late — v1.0 GA unaffected |
| QA fixtures complete | QA + Product | *Can accumulate through Sprints 1-3 |
| Alpha customer list signed | Product | None — Phase 1 blocked without them |
| Beta customer list signed | Product | *Can grow through Sprints 1-6 |
| Consolidated risk register with runbooks for 8 priority risks | Founder + Eng Lead | *Runbooks for lower priorities can be written during Sprint 1-3 |
| Kill-switch rehearsal completed on staging within 60-second SLO | DevOps + Eng Lead | None — must be proven before customer traffic |
| Sprint 1 and Sprint 2 tickets pre-written in the tracker | Eng Lead + PM | None — otherwise Week 9 starts with a planning meeting instead of code |

## 14.3 The go/no-go meeting

- Held on Wednesday of Week 8 — leaves Thursday-Friday to resolve remaining items or accept the slip.

- Attendees: Founder, Engineering Lead, Product Manager, DevOps Lead, Legal Counsel (or written statement), Designer.

- Duration: 90 minutes maximum. If it runs longer, the answer is No-Go by default.

- Format: walk the checklist above; each row gets Yes / No / Workaround.

- Decision: unanimous Go required from Founder + Engineering Lead. Any No-Go from either is a slip.

- Output: a signed one-page memo — Go with any signed-off workarounds, OR No-Go with the specific blockers and the revised kickoff date.

## 14.4 If it's a No-Go

- Slip by 1 week — acceptable, run planning for one more week.

- Slip by 2-4 weeks — acceptable but triggers a scope conversation; something may descope from v1.0 to v1.1.

- Slip by more than 4 weeks — treat as a serious planning failure; run a root-cause review before continuing.

## 14.5 If it's a Go

- Sprint 1 begins Monday of Week 9.

- The handoff package is broadcast to the whole team (engineering + adjacent stakeholders).

- The planning cadence (weekly product meetings, weekly vendor check-ins) shifts to sprint cadence.

- Workstreams A-I close; ownership of ongoing items (vendor management, legal follow-ups, risk register) transfers to permanent owners.

- The build is measured against the v1.0 rollout plan (v1.0 Section 19) from this point.

## 14.6 Closing note

The pre-production planning phase feels expensive because eight weeks with no code makes people uncomfortable. It is nearly always cheaper than the alternative — starting code the week the spec is done and hitting a wall in Sprint 3 because a provider is still in review, or the legal position is unclear, or the corpus is still on a hard drive somewhere, or nobody is on-call for the safety scanner going haywire.

The Engagement service in v0.3 hit its numbers because the audit was done before launch, not after. Studio is a substantially larger service. Give the pre-production work the eight weeks it needs. The build after it will move faster than one that skipped this phase — reliably.

If any part of this playbook fails to translate to reality, revise it. The goal is a running v1.0 with the fewest surprises, not a perfectly-followed plan.